## Slide 1: Penelitian Cloud Provisioning
Minute of Meeting
18 Juli 2022

## Slide 2: Anggota Tim
Dosen
Ir. Ary Mazharuddin Shiddiqi, S.Kom., M.Comp.Sc., Ph.D (AM)
Dr. Diana Purwitasari, S.Kom., M.Sc. (DP)
Henning Titi Ciptaningtyas, S.Kom, M.Kom. (HC)
Ridho Rahman Hariadi, S.Kom., M.Sc. (RR)
Annisaa Sri Indrawanti, S. Kom., M. Kom (AS)
mahasiswa
05311940000021 - Bryan Yehuda Mannuel (BY)
05311940000010 - Widya Inayatul Luthfiyah (WI)

## Slide 3: Agenda Rapat
Pengenalan Anggota Tim
Jobdesc Anggota Tim
Latar Belakang
Target Penelitian
Timeline Kegiatan
Detil Penelitian – Algoritma
Detil Penelitian – Dataset
Detil Penelitian – Tools

## Slide 4: Jobdesc
No | Kegiatan | PIC
1 | Konsep Penelitian | HC, AM, DP
2 | Implementasi GA-ANN | BY, disupervisi HC, RR
3 | Implementasi OBL-SSA | WI, disupervisi HC, RR
4 | Pengumpulan data ujicoba | BY, WI, HC, RR, AS
5 | Analisa dan penarikan kesimpulan | HC, disupervisi AM, DP
6 | Penulisan artikel jurnal | HC
7 | Reviewer artikel jurnal | AM, DP

## Slide 5: Latar Belakang

## Slide 6: Target
IJIES (International Journal of Intelligent Engineering and Systems) journal
Submitted December 2022
So, aplikasi diharapkan selesai November awal.

## Slide 7: Timeline Kegiatan Mahasiswa
Kegiatan | Minggu |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Pembuatan Proposal TA | √ |  |  |  |  |  |  |  |  |  |  | 
Belajar cloudsim melalui tutorial online | √ | √ |  |  |  |  |  |  |  |  |  | 
Pembuatan aplikasi GA - ANN OBL-SSA |  | √ | √ | √ | √ | √ | √ | √ |  |  |  | 
Ujicoba aplikasi menggunakan dataset 1 dan 2 |  |  |  |  |  | √ | √ | √ | √ |  |  | 
Analisa hasil uji coba |  |  |  |  |  |  |  | √ | √ | √ |  | 
Penulisan laporan TA |  |  |  |  |  |  |  |  |  | √ | √ | √
Dimulai dari akhir Juli 2022

## Slide 8: Detil Penelitian – Algoritma GA-ANN
Paper rujukan
 GA original
 GA-ANN

## Slide 9: Detil Penelitian – Algoritma OBL-SSA
Paper rujukan
 SSA original
 OBL-SSA

## Slide 10: Detil Penelitian – Dataset
Buatan
VM:
    3 types of VM
    MIPS / proc: 400, 500, 600
    RAM (MB): 512, 1024, 2048
Datacenter
    6 Datacenter: D1 – D6
    1,000,000 GB memory, 128 GB RAM
    6 processsors, 3 host, 4 core
SDSC Horizon
https://www.cs.huji.ac.il/labs/parallel/workload/l_sdsc_blue/index.html

## Slide 11: Detil Penelitian – Data eksperimen yg dikumpulkan
Performance Metrics Average Start Time
Performance Metrics Average Finish Time
Performance Metrics Execution Time
Performance Metric Completed Tasks
Performance Metric Fault Rate

## Slide 12: Detil Penelitian – Tools
Cloudsim – Link tutorial (15 jam)
  https://www.udemy.com/course/learn-basics-of-cloudsim/learn/lecture/11495798?start=0#overview
  Username: henning.its@gmail.com
  Password: UdemyHenning
Eclipse